## Sheet1
Tasks | Start Date | End Date
Several meeting with Penny Everettt to discuss good practise and software | 2006-10-26 | 2007-01-15
Spent two weeks preparing the learning agreement. Searched on line for sample. Spoke to CN who encourage me to write down what I was going to do/ hoped to achieve and then write draft. Wrote the 500 word project brief using each learning outcome for each paragraph. Word count 504. Draft learning agreement reading for CN to proof 8/11.
Get Penny to check online learning module and adminster mouse function, disable keyboard function | 2006-10-31 | 2007-11-30
Meet with Employer to discuss requirements | 2006-11-01 | 2006-11-08
Write learning agreement | 2006-11-08 | 2006-11-15
Recommended reading - 4 books and some websites (check out LTSS bookshelves) | 2006-11-15 | 2007-01-15
Hand in draft learning agreement | 2006-11-20 | 2006-11-20
Decide on topic/ order/ how information will be tested | 2006-11-22 | 2006-11-29
Create storyboard | 2006-11-29 | 2006-12-06
Meeting with Penny Everett to discuss storyboard
Show storyboard to employer | 2006-12-06 | 2006-12-06
Work on online learning materials | 2006-11-21 | 2006-12-11
Hand in completed learning agreement | 2006-12-11 | 2006-12-11
Create the online learning materials | 2006-12-13 | 2007-01-08
Meeting with Penny Everett to discuss online learning mateirals
Show online learning materials to employer | 2007-01-08 | 2007-01-15
Website Accessibility workshop | Saturday 13th January 2007 | Saturday 13th January 2007
Test online learning materials | 2007-01-01 | 2007-03-01
Meeting with Penny Everett - speak to about outcome of online learning materials
Rework online learning materials | 2007-02-01 | 2007-03-01
Meeting with Penny Everett - speak to
End of module presentation - at University College London | April 2007 - date TBC | Enter date in diary when completed
Portfolio submission | 2007-05-04 | 2007-05-04